## Sheet1
Poornima College of Engineering Department of Information Technology Product Backlog (Product-II:2018-19)
Epic | Sprint | User Story Role | User Story Details | Story Details | Task Items | Analyst/Prep Work | Dev. Estimate | QA | Total User Story Hours
Event Planning Website | 1 | All User | Create Login Page | All the users can access the website by login into it. | 1. Create a Login Page | 2 | 50 | 4 | 56
2. Connect it to database
3. Verify User name and password
4. It it is correct redirect to the home page
5. If it is incorrect redirect to the forget password page
Event Planning Website | 2 | Volunteer | Create Volunteer's Module | Volunteer can perform his related operations into this page | 1. Login to the website | 2 | 50 | 5 | 57
2. Fill the registration details into the registration page
3. Reset the password
4. Select the particular Event for applying as a volunteer
5. Apply as a volunteer in the particular event
6. Check the status
Event Planning Website | 3 | Manager | Manage Volunteer's Module | Manager will manage the activities of volunteer through this module | 1. Login to the website | 1 | 25 | 3 | 29
2. Approve volunteer's request
3. Post an event invite for volunteer
4. Conduct Stand up meetings
5. Perform documentation work
Event Planning Website | 4 | Manager | Manage Cusrtomer's Module | Manager will manage the activities of customer through this module | 1. Add the events category | 2 | 45 | 5 | 52
2. Delete the Event category
3. Update the event category
4. Manage the booking of events
5. Manage the event handling team
6. Maintain the details of customers
7. Add approx rates of event categories
8. Accept the request of customer for organising the event
9. Add contact details of manager
Event Planning Website | 5 | End User | Create Customer's Module | Customer can perform his related operations into this page | 1. Sign Up into the website | 1 | 25 | 4 | 30
2. Login to the website
3. Select the Event Category
4. Fill his details- Name, address, email-id and contact number
5. View the rates of event categories
Total Hours | [5 empty] | 8 | 195 | 21 | 224
Ms. Shazia Haque Ayushi Sharma (Project Guide) (Scrum Master) Mr. Shirish Nagar (Project Coordinator)